## Team Roles
TEAM ROLES ¦ KMS DELIVERY REVIEW
Responsibilities are organizational hats, not 44 required employees. Independently accountable reviewers and trustees cannot certify their own implementation.
Role ID | Family | Specialist responsibility | Mission / authority | Expected deliverable | Engagement | When needed | Named individual | Staffing status
R01 | Strategy & delivery | Executive sponsor | Own business case, funding, risk appetite and final business authorization. | Approved charter; budget envelope; risk acceptance boundaries. | Decision-maker | All |  | Unassigned
R02 | Strategy & delivery | Holding-company governance chair | Resolve conflicts between group oversight and subsidiary autonomy. | Group governance policy; escalation and veto process. | Decision-maker | All |  | Unassigned
R03 | Strategy & delivery | Product owner / product director | Own roadmap, value hypotheses, scope, acceptance and product trade-offs. | Product vision; prioritization; signed acceptance criteria. | Core | All |  | Unassigned
R04 | Strategy & delivery | Program / delivery manager | Run dependencies, milestones, resourcing, delivery risks and release governance. | Integrated program plan; RAID log; gate evidence pack. | Core | All |  | Unassigned
R05 | Strategy & delivery | Business analyst / requirements engineer | Convert workflows into detailed, testable specifications across entities. | Process maps; user stories; traceability; acceptance scenarios. | Core | Discovery–release |  | Unassigned
R06 | Strategy & delivery | Enterprise architect | Ensure integration with IT strategy, identity estate and governance framework. | Architecture principles; capability map; integration boundaries. | Core / fractional | Discovery–design |  | Unassigned
R07 | Strategy & delivery | Solution architect / technical lead | Own system-wide design, architecture decision records and interfaces. | Threat-aware architecture; API boundaries; ADRs. | Core | Design–release |  | Unassigned
R08 | Strategy & delivery | FinOps / financial analyst | Model storage, compute, OCR, AI, network egress, keys and long-term cost. | TCO model; tenant chargeback and budget guardrails. | Fractional | Planning–operations |  | Unassigned
R09 | Strategy & delivery | Procurement and third-party risk lead | Assess IdP, hosting, KMS, converters, AI and signature vendors. | Vendor due diligence; DPAs; exit conditions and SLAs. | Fractional | Design–operations |  | Unassigned
R10 | Strategy & delivery | Change and adoption manager | Lead stakeholder engagement, phased rollout, communications and training. | Adoption plan; pilot feedback; organizational readiness. | Core / fractional | Pilot–operations |  | Unassigned
R11 | Business & information | Subsidiary representatives / UAT leads | Represent each company and validate delegated administration workflows. | 10-tenant UAT scenarios; local policy signoffs. | Distributed business owners | Discovery–pilot |  | Unassigned
R12 | Business & information | Records and information governance lead | Own classification, controlled records, retention, legal holds and disposition. | File plan; schedules; disposition protocol; audit evidence. | Required domain owner | Design–operations |  | Unassigned
R13 | Business & information | Legal counsel and eDiscovery specialist | Define statutory records, electronic evidence and contractual sharing rights. | Jurisdiction matrix; legal holds; signature rules; disclosure playbooks. | Specialist / legal signoff | Design–operations |  | Unassigned
R14 | Business & information | Privacy officer / DPO | Resolve controller/processor duties, minimization, transfers and subject requests. | DPIA; lawful-basis map; erasure and transfer procedures. | Independent oversight | Design–operations |  | Unassigned
R15 | Business & information | Knowledge architect / taxonomy specialist | Structure wiki, canonical policy knowledge, metadata quality and ownership. | Taxonomy; editorial governance; content quality indicators. | Core / fractional | Design–operations |  | Unassigned
R16 | Business & information | UX researcher / product designer | Design usable multi-tenant workflows and high-stakes warnings. | Journey maps; interaction prototypes; usability research. | Core | Discovery–release |  | Unassigned
R17 | Business & information | Localization lead and 13-language reviewers | Own locale glossary, native review, RTL, linguistic correctness. | Locale specification; translation memory; signoff for 13 languages. | Specialists; not 13 full-time staff | Design–release |  | Unassigned
R18 | Business & information | Accessibility specialist | Measure keyboard, screen-reader, cognitive and bidirectional usability. | WCAG 2.2 AA audit; manual assistive-technology reports. | Specialist / independent test | Design–release |  | Unassigned
R19 | Security & assurance | Application security and threat-model architect | Threat-model every entry point, isolation boundary and document operation. | Threat model; abuse cases; ASVS verification mapping. | Core / independent review | Design–operations |  | Unassigned
R20 | Security & assurance | Cryptographic protocol engineer | Design E2EE, recipient identity, keys, recovery and algorithm agility. | Protocol design; test vectors; client integrity assumptions. | Specialist; critical | Design–security acceptance |  | Unassigned
R21 | Security & assurance | IAM / PAM architect | Own SSO, SCIM, tenant memberships, policy evaluation and privilege boundaries. | Identity model; policy decision specification; SoD rules. | Core / specialist | Design–operations |  | Unassigned
R22 | Security & assurance | Cloud and platform security engineer | Harden storage, KMS, network, secret handling, workloads and tenancy. | Least privilege policies; hardening baselines; attack-path tests. | Core / specialist | Design–operations |  | Unassigned
R23 | Security & assurance | SOC and incident-response lead | Define detection, triage, containment, evidence and breach notifications. | Detection rules; playbooks; response exercises. | Operational owner | Pilot–operations |  | Unassigned
R24 | Security & assurance | Independent penetration tester / red team | Attempt cross-tenant access, WordPress takeover and lateral movement. | Independent findings; retest attestation; exploit-based proof. | Independent; release-blocking | Pre-release & periodic |  | Unassigned
R25 | Security & assurance | Independent cryptography/security assessor | Challenge protocol, device trust, key recovery and claims independently. | Assurance report; review of threat model and test vectors. | Independent; release-blocking | Design & pre-release |  | Unassigned
R26 | Security & assurance | Key recovery trustee / custodial committee | Approve exceptional key recovery with quorum and conflict-of-interest controls. | Trustee roster; dual-control runbook; recovery drill evidence. | Operational; separate from engineering | Pilot–operations |  | Unassigned
R27 | Security & assurance | Compliance / internal audit lead | Assess control design and effectiveness, evidence and audit independence. | Control matrix; exception register; audit plan. | Oversight / independent | Design–operations |  | Unassigned
R28 | Product engineering | WordPress plugin engineer | Build low-privilege integration, admin links, secure upgrades and REST bridge. | Signed plugin; WP capability boundaries; upgrade tests. | Core | Build–operations |  | Unassigned
R29 | Product engineering | Backend and API engineer | Implement tenants, entitlements, document and lifecycle APIs. | Versioned API; authorization middleware; event flows. | Core, multiple | Build–operations |  | Unassigned
R30 | Product engineering | Web frontend engineer | Build dashboards, dialogs, document workflows and accessibility. | Responsive, internationalized web client and component library. | Core, multiple | Build–operations |  | Unassigned
R31 | Product engineering | Data architect / database engineer | Define tenant isolation, metadata evolution, transactions and query controls. | Logical model; isolation constraints; data lifecycle design. | Core | Design–operations |  | Unassigned
R32 | Product engineering | Storage, conversion and file-processing engineer | Build encrypted object paths, import pipeline and sandboxed previews. | Storage adapters; scanning/quarantine; conversion sandboxes. | Core | Build–operations |  | Unassigned
R33 | Product engineering | Workflow / business-process engineer | Implement state machines, approval delegation, retries and audit binding. | Versioned workflow engine; simulation and escalation tests. | Core / specialist | Build–operations |  | Unassigned
R34 | Product engineering | Search / information retrieval engineer | Handle metadata search, multilingual analyzers and mode-appropriate indexing. | Search design; relevance evaluation; index isolation tests. | Specialist | Enterprise phase |  | Unassigned
R35 | Product engineering | AI / ML engineering lead | Build permission-trimmed retrieval, evaluation, output controls and provider policy. | AI risk tests; grounded retrieval; model and cost governance. | Specialist | Enterprise phase |  | Unassigned
R36 | Product engineering | Integration / connector engineer | Build OIDC/SAML/SCIM, M365, webhooks and enterprise connectors. | Connector contracts; event replay; permission mapping tests. | Core / specialist | Build–operations |  | Unassigned
R37 | Product engineering | Trusted-client and mobile/desktop engineer | Build independent signed client, E2EE device enrollment, offline protection. | Trusted client; release signing; platform key storage and sync tests. | Core; critical for E2EE | Design–operations |  | Unassigned
R38 | Product engineering | DevOps / platform engineer | Build infrastructure-as-code, CI/CD, isolated environments and delivery chain. | IaC; provenance; scans; rollback and deployment pipelines. | Core | Build–operations |  | Unassigned
R39 | Product engineering | SRE / disaster-recovery engineer | Engineer SLOs, backup recoverability, observability and controlled restoration. | SLO design; RTO/RPO drills; runbooks; capacity forecasts. | Core / specialist | Build–operations |  | Unassigned
R40 | Product engineering | QA automation / test architect | Own unit, integration, security regression, contract and E2E coverage. | Test pyramid; requirement-to-test traceability; release reports. | Core, multiple | Build–operations |  | Unassigned
R41 | Product engineering | Performance / capacity engineer | Test upload, search, 10-tenant concurrency, worst-case workflows. | Load model; benchmarks; capacity limits and budgets. | Specialist | Before pilot & scale |  | Unassigned
R42 | Product engineering | Migration and data-quality engineer | Move legacy documents, ACLs, versions and metadata without leakage. | Dry-run reports; integrity manifests; reconciliation. | Specialist | Pilot–rollout |  | Unassigned
R43 | Product engineering | Technical writer and training designer | Explain end-user actions, admin policies, supported security modes and limits. | Product documentation; API docs; localized training materials. | Specialist | Build–operations |  | Unassigned
R44 | Product engineering | Support / customer success engineer | Design safe diagnostics, support access and long-term service adoption. | Support playbooks; escalation; no-plaintext debug tools. | Operational | Pilot–operations |  | Unassigned

## Module Ownership
MODULE OWNERSHIP ¦ KMS DELIVERY REVIEW
One accountable domain role per module; delivery and independent review must be separated on high-assurance features. All 22 modules tie to the 346-feature baseline.
Module | Features | Module focus | Accountable | Build leads | Required reviewers | Incorporate into design | Release acceptance evidence | Risk tier | Review status
TEN | 14 | Tenant governance / subsidiaries | R02 | R07, R29, R31 | R11, R12, R21, R19 | Model legal company boundaries, groups and project spaces separately; prohibit implicit holding-admin document access; apply group minimum policies without silent privilege expansion; isolate DB, object storage, queues, search, logs, backups, and caches; design mergers/splits as supervised migrations. | A cross-tenant user, cache key, search request, export job or backup restore never reveals unauthorized tenant material. | Critical | Unreviewed
IAM | 17 | Membership, roles and policy | R21 | R29, R31, R30 | R02, R19, R11, R27 | Formalize RBAC + ABAC + ACL evaluation order, global hard-deny, explicit deny, inheritance and policy versioning; enforce separation of duties; prevent self-grants and delegation loops; invalidate permissions in jobs, URLs and offline clients; provide decision explanations without leaking titles. | For each permission state, API, previews, exports, mobile, workers and search enforce the same decision after revocation. | Critical | Unreviewed
AUT | 13 | Authentication and devices | R21 | R36, R37, R29 | R19, R22, R23, R14 | Use enterprise IdP and phishing-resistant factors for privileged access; separate WordPress and document-service sessions; map IdP identity to immutable tenant memberships; lifecycle-sync join/move/leave; sign and verify E2EE device public keys; specify lost-device and IdP-outage handling. | Compromised WordPress cookies cannot mint a document-system privileged identity or enroll an unapproved E2EE device. | Critical | Unreviewed
DOC | 22 | Document capture and lifecycle | R03 | R32, R29, R31 | R12, R19, R20, R11 | Version documents immutably with content integrity and provenance; quarantine new uploads; validate type by content; sandbox all converters; make document metadata, previews and exports classification-aware; guarantee idempotency and quota enforcement on resumable uploads. | Malformed file, aborted upload, version race or failed scan cannot expose partially processed plaintext or bypass approval. | Critical | Unreviewed
MET | 16 | Metadata, taxonomy and search | R15 | R34, R31, R29 | R20, R14, R17, R19 | Version metadata schemas and taxonomies; specify encrypted/public fields and side-channel leakage budgets; tenant-scope autosuggest, indexes, caches and analytics; support locale-specific word segmentation; keep E2EE content search on trusted clients or explicitly approved leakage-limited protocols. | Search returns only authorized resources and cannot reveal confidential filenames, snippets or existence through autocomplete. | High | Unreviewed
COL | 16 | Editing and collaboration | R03 | R30, R29, R37 | R20, R12, R19, R18 | Separate draft collaboration from immutable approved record; resolve locks, autosaves, failed merges and approvals; sandbox third-party editors; make E2EE collaborative editing a separate approved protocol; treat watermarks and screenshot controls as deterrents, not guarantees. | Unauthorized reviewer cannot change an approved hash or gain editor plaintext through preview/editor callback. | High | Unreviewed
KNO | 16 | Knowledge management / wiki | R15 | R30, R29, R34 | R11, R12, R17, R18 | Assign content steward and periodic validation; separate canonical policies from discussion threads; enforce link traversal rights; maintain multilingual article versions and fallback markers; prove read-and-attest evidence binds a specific version and language. | Users see only permitted linked knowledge; acknowledgment is linked to exact approved revision, not mutable draft. | High | Unreviewed
WFL | 19 | Workflow and approvals | R03 | R33, R29, R30 | R21, R12, R13, R19 | Design versioned state machines with explicit retry/idempotency semantics; enforce maker/checker, approval quorum and delegated-authority limits; bind approval to document hash/policy; protect confidential notification payload; distinguish internal approval from legally qualified e-signature. | Workflow cannot be self-approved through race conditions, delegation cycles, replayed jobs or version swaps. | High | Unreviewed
REC | 18 | Records, holds, eDiscovery | R12 | R29, R31, R32 | R13, R14, R20, R27 | Capture jurisdictional retention rules, classification events, WORM scopes and legal hold precedence; define conflicts with subject erasure, backups and cryptographic deletion; assess whether E2EE discovery requires trustee-based access or custodian-driven client export. | Hold blocks destructive operations across versions, exports, backup expiry and crypto-erasure until lawfully released. | Critical | Unreviewed
ENC | 20 | Encryption / keys / E2EE | R20 | R37, R32, R29 | R25, R19, R21, R26 | Independent trusted code distribution must withstand a WordPress breach; use reviewed AEAD and per-version keys, authenticated document context, verified recipient identities, rekey and recovery models; explicitly expose recovery-vs-zero-access trade-off; test WordPress takeover. | External reviewers reproduce crypto vectors; simulated WordPress RCE cannot decrypt protected records or forge recipients. | Critical | Unreviewed
SEC | 16 | Threat prevention and detection | R19 | R22, R23, R28 | R24, R25, R27, R14 | Threat-model tenant enumeration, malicious file parsing, SSRF, DLP gaps, supply-chain compromise, secrets leakage and abuse; segregate malware scanners and audit pipelines; produce signed SBOM/release provenance and vulnerability response process. | A full red-team sequence includes cross-tenant, malicious-file, compromised plug-in and service-credential compromise. | Critical | Unreviewed
EXT | 13 | Guests, sharing, data rooms | R03 | R29, R37, R30 | R13, R14, R20, R21 | Verify external key ownership and legal recipient identity; require source-tenant consent for intercompany disclosure; set expiry, purpose, review and download policy; prevent cross-bidder leakage; treat guest offboarding and past downloads separately. | Sharing to Subsidiary B never creates blanket rights for B or leaks material via email or data-room logs. | High | Unreviewed
RPT | 14 | Audit, oversight and analytics | R27 | R29, R31, R23 | R14, R12, R19, R02 | Write independently retained and integrity-protected events; choose event schema, clock synchronization and redaction; separate subsidiary record-level audit from group aggregate reporting; limit queryable metadata to avoid inference; define audit retention and regulator access. | Neither WordPress admin nor subsidiary admin can erase evidence of their access or infer confidential sibling tenants. | Critical | Unreviewed
AIX | 17 | AI and decision support | R03 | R35, R34, R29 | R14, R20, R19, R13 | Default deny on highly classified material and E2EE server inference; permission-check at retrieval and generation, not just indexing; protect embeddings, prompts and outputs; defend prompt injection, track models/providers, evaluate accuracy by language; require human approval for consequential decisions. | Revoked document cannot appear in RAG retrieval, answer citations, embeddings or cached model responses. | High | Unreviewed
L10 | 15 | 13 languages and accessibility | R17 | R30, R37, R43 | R18, R16, R11, R15 | Native review for English, Persian, French, Turkish, Russian, Simplified Chinese, German, Portuguese, Spanish, Hindi, Japanese, Arabic and Armenian; define regional variants; handle Unicode normalization, RTL text mixing, calendars/time zones, plural forms, fonts and WCAG 2.2 AA. | Every core journey passes native-speaker QA and keyboard/screen-reader testing in both RTL and LTR. | High | Unreviewed
API | 17 | External APIs and connectors | R07 | R36, R29, R28 | R21, R19, R22, R09 | Minimize WordPress bridge privileges; enforce tenant-scoped token audiences and expiry; sign webhooks with replay controls; make retries idempotent; version schemas; prohibit connectors from bypassing legal holds, classification or encryption mode. | Forged webhook, compromised plugin, tenantless API key or connector replay cannot perform forbidden operations. | Critical | Unreviewed
UX | 13 | Experience and productivity | R16 | R30, R37 | R18, R17, R11, R20 | Use unmistakable tenant context and confidentiality-mode cues; explain why an action is denied without disclosing resources; support safe bulk operations, escape hatches, accessible approvals and reliable upload progress; ensure privacy of notifications and recent-item widgets. | Usability sessions show administrators do not mistake group-wide authority for permission to view subsidiary content. | High | Unreviewed
MOB | 12 | Mobile, desktop and offline | R37 | R30, R36, R39 | R20, R21, R22, R18 | Implement signed app updates, hardware-backed local secrets where supported, lost-device offboarding, cache quotas, offline expiry, sync conflicts and remote wipe best-effort warnings; test independent trust from WordPress and 13-language UI. | Offline user cannot access never-synced files or new versions after revocation; limitations for existing cached files are documented. | High | Unreviewed
PRV | 14 | Privacy, residency and compliance | R14 | R29, R31, R39 | R13, R12, R27, R09 | Identify controller/processor relationships per legal entity, data maps and subprocessors; configure regional storage and key access; reconcile privacy requests with holds; scope analytics; assess incident notification duties and lawful cross-border transfers before deployment. | Requests for access, deletion, export and residency evidence complete with recorded lawful exceptions and approvals. | Critical | Unreviewed
OPS | 21 | Operations, backup and resilience | R39 | R38, R22, R40 | R23, R25, R08, R27 | Define measurable SLO/RTO/RPO by mode, region and tier; verify restoration of data plus recovery keys and permissions; apply infrastructure isolation, immutable backups, provenance signing and supply-chain scanning; run incident, disaster and tenant-departure drills. | Restore 10-tenant representative backup without orphaning keys, violating residency, or resurrecting revoked access. | Critical | Unreviewed
MIG | 13 | Migration and rollout | R10 | R42, R36, R40 | R11, R12, R14, R17 | Inventory legacy records and ACLs, verify metadata semantics, create resumable staging, quarantine unsafe files and check chain of custody; reconcile identity conflicts; pilot at least two subsidiaries with different policies and a representative RTL language. | Signed migration manifest shows all versions, records, holds and ACLs reconciled before cutover. | High | Unreviewed
VRP | 10 | Vertical enterprise modules | R03 | R33, R29, R30 | R13, R12, R11, R20 | Treat board, HR, contracts, quality and procurement as separate domain workflows with distinct legal policies and confidentiality needs; define modular extension API, isolation rules and independent threat review for each added module. | A new vertical extension cannot change another tenant’s policies or obtain zero-knowledge plaintext by default. | Medium | Unreviewed

## Feature Traceability
FEATURE TRACEABILITY ¦ KMS DELIVERY REVIEW
346 original requirement IDs preserved from the existing Blueprint. Assign individual owners, attach tests and set implementation status without losing baseline priority.
Feature ID | Module | Existing feature | Baseline priority | Baseline release | Accountable role | Build responsible | QA lead | Review | Implementation state | Acceptance test link | Module risk
TEN-01 | TEN | Holding-company hierarchy | MUST | CORE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-02 | TEN | Tenant provisioning | MUST | CORE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-03 | TEN | Tenant suspension and closure | MUST | CORE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-04 | TEN | Tenant-level quotas | SHOULD | ENTERPRISE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-05 | TEN | Independent administration | MUST | CORE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-06 | TEN | Central policy baselines | MUST | CORE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-07 | TEN | Cross-subsidiary projects | SHOULD | ENTERPRISE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-08 | TEN | Tenant context selector | MUST | CORE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-09 | TEN | Tenant-specific storage partitions | MUST | CORE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-10 | TEN | Tenant export and portability | SHOULD | ENTERPRISE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-11 | TEN | Tenant-specific legal identity | SHOULD | ENTERPRISE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-12 | TEN | Multi-company organizational reporting | SHOULD | ENTERPRISE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-13 | TEN | Tenant residency and region selection | SHOULD | ENTERPRISE | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
TEN-14 | TEN | Corporate reorganizations | ADVANCED | EXPANSION | R02 | R07, R29, R31 | R40 | R24 | Not started |  | Critical
IAM-01 | IAM | Global identities with tenant memberships | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-02 | IAM | Subsidiary-defined custom roles | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-03 | IAM | Role hierarchies and constraints | SHOULD | ENTERPRISE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-04 | IAM | Department and project groups | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-05 | IAM | Document-level ACLs | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-06 | IAM | Attribute-based rules | SHOULD | ENTERPRISE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-07 | IAM | Folder permission inheritance | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-08 | IAM | Policy simulator | SHOULD | ENTERPRISE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-09 | IAM | Access request and approval | SHOULD | ENTERPRISE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-10 | IAM | Time-limited and conditional permissions | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-11 | IAM | Separation of duties | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-12 | IAM | Delegated administration | SHOULD | ENTERPRISE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-13 | IAM | Emergency break-glass | SHOULD | ENTERPRISE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-14 | IAM | Service accounts and workloads | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-15 | IAM | Group-wide permission inventory | SHOULD | ENTERPRISE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-16 | IAM | Periodic access certification | SHOULD | ENTERPRISE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
IAM-17 | IAM | Authorization race protection | MUST | CORE | R21 | R29, R31, R30 | R40 | R24 | Not started |  | Critical
AUT-01 | AUT | Enterprise SSO | MUST | CORE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-02 | AUT | Passkeys and MFA | MUST | CORE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-03 | AUT | Local account fallback | SHOULD | ENTERPRISE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-04 | AUT | Lifecycle synchronization | SHOULD | ENTERPRISE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-05 | AUT | Sessions and refresh token controls | MUST | CORE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-06 | AUT | Trusted device policy | SHOULD | ENTERPRISE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-07 | AUT | Session inventory | MUST | CORE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-08 | AUT | Adaptive authentication | SHOULD | ENTERPRISE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-09 | AUT | Privileged access controls | SHOULD | ENTERPRISE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-10 | AUT | Account takeover defenses | MUST | CORE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-11 | AUT | Trusted device enrollment for E2EE | MUST | CORE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-12 | AUT | Credential and session recovery | MUST | CORE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
AUT-13 | AUT | Guest identity federation | SHOULD | ENTERPRISE | R21 | R36, R37, R29 | R40 | R24 | Not started |  | Critical
DOC-01 | DOC | Upload and download | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-02 | DOC | Large and resumable uploads | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-03 | DOC | Common business formats | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-04 | DOC | Folder hierarchy and libraries | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-05 | DOC | Document templates | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-06 | DOC | Document registration | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-07 | DOC | Batch upload and tagging | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-08 | DOC | Automated email ingestion | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-09 | DOC | Scanner and capture integration | ADVANCED | EXPANSION | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-10 | DOC | Document status lifecycle | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-11 | DOC | Document ownership and custodian | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-12 | DOC | Move, copy and link | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-13 | DOC | Recycle bin and restoration | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-14 | DOC | Duplicates and fingerprinting | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-15 | DOC | Integrity verification | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-16 | DOC | Metadata-only records | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-17 | DOC | Document bundles and dossiers | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-18 | DOC | Controlled document numbering | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-19 | DOC | File size and type policy | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-20 | DOC | Document expiration and review | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-21 | DOC | Protected previews | MUST | CORE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
DOC-22 | DOC | Content redaction | SHOULD | ENTERPRISE | R03 | R32, R29, R31 | R40 | R24 | Not started |  | Critical
MET-01 | MET | Custom metadata schemas | MUST | CORE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-02 | MET | Required and conditional metadata | MUST | CORE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-03 | MET | Controlled vocabularies | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-04 | MET | Saved views and smart folders | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-05 | MET | Advanced metadata search | MUST | CORE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-06 | MET | Full-text indexing in managed mode | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-07 | MET | Zero-Knowledge discovery | MUST | CORE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-08 | MET | OCR and extraction | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-09 | MET | Multilingual search | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-10 | MET | Document relationships | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-11 | MET | Knowledge graph and lineage | ADVANCED | EXPANSION | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-12 | MET | Duplicate topic detection | ADVANCED | EXPANSION | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-13 | MET | Search relevance tuning | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-14 | MET | Search history and favorites | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-15 | MET | Content provenance | MUST | CORE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
MET-16 | MET | Information-quality indicators | SHOULD | ENTERPRISE | R15 | R34, R31, R29 | R40 | R19 / R40 | Not started |  | High
COL-01 | COL | Immutable version history | MUST | CORE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-02 | COL | Major and minor revisions | SHOULD | ENTERPRISE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-03 | COL | Version comparison | SHOULD | ENTERPRISE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-04 | COL | File locking and checkout | MUST | CORE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-05 | COL | Browser editing | SHOULD | ENTERPRISE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-06 | COL | Real-time coauthoring | ADVANCED | EXPANSION | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-07 | COL | Inline comments and replies | MUST | CORE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-08 | COL | Annotations and highlights | SHOULD | ENTERPRISE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-09 | COL | Suggested edits and change requests | SHOULD | ENTERPRISE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-10 | COL | Review assignments | MUST | CORE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-11 | COL | Document subscriptions | SHOULD | ENTERPRISE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-12 | COL | Watermarking and visual labels | SHOULD | ENTERPRISE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-13 | COL | Offline edit conflict handling | ADVANCED | EXPANSION | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-14 | COL | Approval signatures | MUST | CORE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-15 | COL | Discussion and reactions | SHOULD | ENTERPRISE | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
COL-16 | COL | Collaborator presence | ADVANCED | EXPANSION | R03 | R30, R29, R37 | R40 | R19 / R40 | Not started |  | High
KNO-01 | KNO | Rich knowledge pages | MUST | CORE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-02 | KNO | Knowledge spaces | MUST | CORE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-03 | KNO | Standard knowledge templates | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-04 | KNO | FAQs and troubleshooting | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-05 | KNO | Subject-matter expert directory | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-06 | KNO | Verified canonical articles | MUST | CORE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-07 | KNO | Learning paths and reading lists | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-08 | KNO | Required reading and attestations | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-09 | KNO | Community contributions | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-10 | KNO | Feedback and knowledge gaps | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-11 | KNO | Decision register | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-12 | KNO | Process and policy maps | ADVANCED | EXPANSION | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-13 | KNO | Knowledge lifecycle | MUST | CORE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-14 | KNO | Multilingual knowledge variants | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-15 | KNO | Audience-tailored homepages | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
KNO-16 | KNO | Knowledge content health | SHOULD | ENTERPRISE | R15 | R30, R29, R34 | R40 | R19 / R40 | Not started |  | High
WFL-01 | WFL | Visual workflow builder | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-02 | WFL | Sequential and parallel approvals | MUST | CORE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-03 | WFL | Conditional routing | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-04 | WFL | Approval policy templates | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-05 | WFL | Task inbox and assignment | MUST | CORE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-06 | WFL | Deadline, SLA and escalation | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-07 | WFL | Approval evidence capture | MUST | CORE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-08 | WFL | Workflow delegation and substitutes | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-09 | WFL | Rejection and revision loops | MUST | CORE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-10 | WFL | Automated metadata actions | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-11 | WFL | Webhook and connector actions | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-12 | WFL | Workflow monitoring | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-13 | WFL | Bulk approval controls | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-14 | WFL | Digital signature integrations | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-15 | WFL | Forms and intake portals | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-16 | WFL | Case and project workflows | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-17 | WFL | Process analytics and improvement | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-18 | WFL | Rule testing and simulation | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
WFL-19 | WFL | Policy exception workflow | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | High
REC-01 | REC | Records classification and file plan | MUST | CORE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-02 | REC | Record declaration and immutability | MUST | CORE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-03 | REC | Event-based retention | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-04 | REC | Multiple overlapping policies | MUST | CORE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-05 | REC | Litigation and investigation holds | MUST | CORE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-06 | REC | Legal hold notification and acknowledgment | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-07 | REC | Disposition review | MUST | CORE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-08 | REC | Disposition certificates | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-09 | REC | WORM or object-lock support | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-10 | REC | Retention clock simulation | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-11 | REC | Controlled archives | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-12 | REC | Legal case repository | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-13 | REC | Discovery search and exports | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-14 | REC | Chain of custody | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-15 | REC | Privacy deletion requests | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-16 | REC | Retention for comments, messages and AI artifacts | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-17 | REC | Paper and hybrid records | ADVANCED | EXPANSION | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
REC-18 | REC | Policy record registers | SHOULD | ENTERPRISE | R12 | R29, R31, R32 | R40 | R25 | Not started |  | Critical
ENC-01 | ENC | Two explicit confidentiality modes | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-02 | ENC | Trusted independent client | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-03 | ENC | Per-version data encryption keys | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-04 | ENC | Client-side encryption and decryption | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-05 | ENC | Envelope encryption in managed mode | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-06 | ENC | Tenant-separated root trust | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-07 | ENC | Recipient and group key wrapping | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-08 | ENC | Key identity transparency | SHOULD | ENTERPRISE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-09 | ENC | Key sharing across subsidiaries | SHOULD | ENTERPRISE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-10 | ENC | Key rotation and compromise response | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-11 | ENC | Zero-knowledge revocation semantics | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-12 | ENC | Key backup and trustee recovery | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-13 | ENC | Key lifecycle inventory | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-14 | ENC | Metadata and filename encryption | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-15 | ENC | Encrypted audit confidentiality | SHOULD | ENTERPRISE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-16 | ENC | Encryption migration and agility | SHOULD | ENTERPRISE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-17 | ENC | Secure temporary data handling | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-18 | ENC | Cryptographic deletion policy | SHOULD | ENTERPRISE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-19 | ENC | Independent crypto review and test vectors | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
ENC-20 | ENC | Key availability and outage behavior | MUST | CORE | R20 | R37, R32, R29 | R40 | R25 + R24 | Not started |  | Critical
SEC-01 | SEC | Data classification model | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-02 | SEC | Data loss prevention rules | SHOULD | ENTERPRISE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-03 | SEC | Download, print and clipboard rules | SHOULD | ENTERPRISE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-04 | SEC | Malware scanning and quarantine | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-05 | SEC | Secure content conversion isolation | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-06 | SEC | Anomaly and insider-risk detection | SHOULD | ENTERPRISE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-07 | SEC | Ransomware detection and rollback | SHOULD | ENTERPRISE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-08 | SEC | External sharing restrictions | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-09 | SEC | Policy-aware watermark and labels | SHOULD | ENTERPRISE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-10 | SEC | Network and IP policy | SHOULD | ENTERPRISE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-11 | SEC | Content security and input hardening | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-12 | SEC | Supply-chain integrity | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-13 | SEC | Security alert operations | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-14 | SEC | Tenant security posture dashboard | SHOULD | ENTERPRISE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-15 | SEC | Abuse-resistant search and APIs | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
SEC-16 | SEC | Vulnerability disclosure and response | MUST | CORE | R19 | R22, R23, R28 | R40 | R24 + R25 | Not started |  | Critical
EXT-01 | EXT | Invitation-based guest access | MUST | CORE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-02 | EXT | Expiring share links | SHOULD | ENTERPRISE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-03 | EXT | External data rooms | SHOULD | ENTERPRISE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-04 | EXT | Recipient-side encryption | MUST | CORE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-05 | EXT | File requests and inbound portals | SHOULD | ENTERPRISE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-06 | EXT | External collaboration expiration | MUST | CORE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-07 | EXT | Controlled outbound packages | SHOULD | ENTERPRISE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-08 | EXT | Inter-subsidiary disclosure agreements | SHOULD | ENTERPRISE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-09 | EXT | Negotiation and external review | ADVANCED | EXPANSION | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-10 | EXT | Public knowledge portal | ADVANCED | EXPANSION | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-11 | EXT | Secure outbound notifications | MUST | CORE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-12 | EXT | Partner audit and attestations | SHOULD | ENTERPRISE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
EXT-13 | EXT | Cross-tenant collaboration reviews | SHOULD | ENTERPRISE | R03 | R29, R37, R30 | R40 | R19 / R40 | Not started |  | High
RPT-01 | RPT | Independent append-only audit events | MUST | CORE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-02 | RPT | Auditable policy decision traces | MUST | CORE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-03 | RPT | Download and view access records | MUST | CORE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-04 | RPT | Tamper-evident event chains | SHOULD | ENTERPRISE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-05 | RPT | Subsidiary dashboards | MUST | CORE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-06 | RPT | Holding oversight dashboard | MUST | CORE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-07 | RPT | Custom report designer | SHOULD | ENTERPRISE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-08 | RPT | Scheduled reporting | SHOULD | ENTERPRISE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-09 | RPT | Security event SIEM export | SHOULD | ENTERPRISE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-10 | RPT | Privacy access ledger | SHOULD | ENTERPRISE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-11 | RPT | Process performance analytics | SHOULD | ENTERPRISE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-12 | RPT | Search and knowledge analytics | SHOULD | ENTERPRISE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-13 | RPT | Compliance evidence package | SHOULD | ENTERPRISE | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
RPT-14 | RPT | Access anomaly visualization | ADVANCED | EXPANSION | R27 | R29, R31, R23 | R40 | R19 / R40 | Not started |  | Critical
AIX-01 | AIX | AI feature policy center | MUST | CORE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-02 | AIX | Permission-trimmed enterprise Q&A | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-03 | AIX | Summarization and document briefs | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-04 | AIX | Semantic and vector search | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-05 | AIX | AI-assisted classification | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-06 | AIX | Entity and obligation extraction | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-07 | AIX | Translation assistance | ADVANCED | EXPANSION | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-08 | AIX | Knowledge article drafting | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-09 | AIX | Duplicate and conflict detection | ADVANCED | EXPANSION | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-10 | AIX | Document question answering | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-11 | AIX | Model and prompt registry | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-12 | AIX | Prompt injection defense | MUST | CORE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-13 | AIX | AI usage audit | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-14 | AIX | Human-in-the-loop guardrails | MUST | CORE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-15 | AIX | Sensitive content redaction before AI | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-16 | AIX | No-training and provider control | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
AIX-17 | AIX | AI accuracy and evaluation suite | SHOULD | ENTERPRISE | R03 | R35, R34, R29 | R40 | R19 / R40 | Not started |  | High
L10-01 | L10 | Thirteen-language interface coverage | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-02 | L10 | Explicit regional locales | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-03 | L10 | Persian RTL layout | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-04 | L10 | Arabic RTL layout | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-05 | L10 | Unicode and filename handling | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-06 | L10 | Translated system notifications | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-07 | L10 | Date, number and calendar localization | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-08 | L10 | Localized metadata labels | SHOULD | ENTERPRISE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-09 | L10 | Language-specific content versions | SHOULD | ENTERPRISE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-10 | L10 | Full text direction testing | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-11 | L10 | Screen-reader and keyboard access | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-12 | L10 | Font and script fallback | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-13 | L10 | Translation workflow | MUST | CORE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-14 | L10 | Localized search behavior | SHOULD | ENTERPRISE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
L10-15 | L10 | Multi-script document production | SHOULD | ENTERPRISE | R17 | R30, R37, R43 | R40 | R18 | Not started |  | High
API-01 | API | Versioned REST API | MUST | CORE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-02 | API | Webhook subscriptions | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-03 | API | OIDC and SAML integration | MUST | CORE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-04 | API | SCIM provisioning | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-05 | API | Microsoft 365 integrations | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-06 | API | Google Workspace integrations | ADVANCED | EXPANSION | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-07 | API | Business platform connectors | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-08 | API | Messaging connectors | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-09 | API | Document editor adapters | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-10 | API | Storage adapter abstraction | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-11 | API | Enterprise search connectors | ADVANCED | EXPANSION | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-12 | API | Event-driven integration bus | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-13 | API | Import and export formats | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-14 | API | Integration marketplace governance | ADVANCED | EXPANSION | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-15 | API | API throttling and metering | MUST | CORE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-16 | API | Developer sandbox and test identities | SHOULD | ENTERPRISE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
API-17 | API | WordPress bridge API | MUST | CORE | R07 | R36, R29, R28 | R40 | R24 | Not started |  | Critical
UX-01 | UX | Role-specific dashboard | MUST | CORE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-02 | UX | Tenant-branded workspace | SHOULD | ENTERPRISE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-03 | UX | Responsive file explorer | MUST | CORE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-04 | UX | Unified task and notification center | MUST | CORE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-05 | UX | Custom dashboard widgets | SHOULD | ENTERPRISE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-06 | UX | Advanced table and bulk actions | SHOULD | ENTERPRISE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-07 | UX | Contextual permissions explanation | SHOULD | ENTERPRISE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-08 | UX | Universal command and quick navigation | SHOULD | ENTERPRISE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-09 | UX | Accessible notification preferences | SHOULD | ENTERPRISE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-10 | UX | Inline help and interactive onboarding | SHOULD | ENTERPRISE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-11 | UX | Personalized saved workspaces | SHOULD | ENTERPRISE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-12 | UX | Keyboard shortcuts and efficiency | ADVANCED | EXPANSION | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
UX-13 | UX | Guided error handling | MUST | CORE | R16 | R30, R37 | R40 | R19 / R40 | Not started |  | High
MOB-01 | MOB | Mobile-responsive secure web application | MUST | CORE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-02 | MOB | Dedicated trusted desktop client | SHOULD | ENTERPRISE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-03 | MOB | Native mobile applications | SHOULD | ENTERPRISE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-04 | MOB | Secure offline access | SHOULD | ENTERPRISE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-05 | MOB | Selective sync and pinning | SHOULD | ENTERPRISE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-06 | MOB | Remote session revocation | MUST | CORE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-07 | MOB | Mobile document capture | SHOULD | ENTERPRISE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-08 | MOB | Push notifications | SHOULD | ENTERPRISE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-09 | MOB | Desktop productivity integrations | ADVANCED | EXPANSION | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-10 | MOB | Certificate and device enrollment | MUST | CORE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-11 | MOB | Low-bandwidth modes | SHOULD | ENTERPRISE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
MOB-12 | MOB | Mobile accessibility and language coverage | MUST | CORE | R37 | R30, R36, R39 | R40 | R19 / R40 | Not started |  | High
PRV-01 | PRV | Privacy by design defaults | MUST | CORE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-02 | PRV | Data processing inventory | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-03 | PRV | Jurisdiction-specific policy profiles | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-04 | PRV | Subject-access and portability requests | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-05 | PRV | Privacy-preserving analytics | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-06 | PRV | Consent and notices | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-07 | PRV | Data residency verification | MUST | CORE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-08 | PRV | Subprocessor and vendor controls | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-09 | PRV | Retention-versus-erasure resolution | MUST | CORE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-10 | PRV | Data classification and impact assessments | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-11 | PRV | Accessibility and inclusion governance | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-12 | PRV | Records of administrator instructions | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-13 | PRV | Document sovereignty and portability | SHOULD | ENTERPRISE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
PRV-14 | PRV | Data breach readiness | MUST | CORE | R14 | R29, R31, R39 | R40 | R27 | Not started |  | Critical
OPS-01 | OPS | Independent secure service deployment | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-02 | OPS | Tenant-aware database architecture | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-03 | OPS | Object-store durability | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-04 | OPS | Availability service-level objectives | SHOULD | ENTERPRISE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-05 | OPS | Recovery time and point objectives | SHOULD | ENTERPRISE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-06 | OPS | Encrypted backup strategy | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-07 | OPS | Immutable and offline backups | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-08 | OPS | Continuous monitoring and alerting | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-09 | OPS | Log correlation and tracing | SHOULD | ENTERPRISE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-10 | OPS | Infrastructure as code | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-11 | OPS | CI/CD security gates | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-12 | OPS | Penetration testing and red teams | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-13 | OPS | Cryptographic threat-model reviews | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-14 | OPS | Performance and load testing | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-15 | OPS | Safe application updates | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-16 | OPS | Configuration and feature flags | SHOULD | ENTERPRISE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-17 | OPS | Support diagnostics | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-18 | OPS | Operations runbooks | MUST | CORE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-19 | OPS | Scalability and partitioning | SHOULD | ENTERPRISE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-20 | OPS | Data restoration and selective recovery | SHOULD | ENTERPRISE | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
OPS-21 | OPS | Service continuity and exit plan | ADVANCED | EXPANSION | R39 | R38, R22, R40 | R40 | R24 | Not started |  | Critical
MIG-01 | MIG | Tenant onboarding wizard | MUST | CORE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-02 | MIG | Legacy file-share import | SHOULD | ENTERPRISE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-03 | MIG | SharePoint and cloud migration | SHOULD | ENTERPRISE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-04 | MIG | Confluence and wiki import | SHOULD | ENTERPRISE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-05 | MIG | Migration dry-run | MUST | CORE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-06 | MIG | User/role mapping review | MUST | CORE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-07 | MIG | Migration integrity manifest | MUST | CORE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-08 | MIG | Pilot and phased rollout | MUST | CORE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-09 | MIG | User training and certification | SHOULD | ENTERPRISE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-10 | MIG | Knowledge migration cleanup | SHOULD | ENTERPRISE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-11 | MIG | Support and help desk integration | SHOULD | ENTERPRISE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-12 | MIG | Documentation and API guides | MUST | CORE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
MIG-13 | MIG | Training sandbox | SHOULD | ENTERPRISE | R10 | R42, R36, R40 | R40 | R19 / R40 | Not started |  | High
VRP-01 | VRP | Contract lifecycle management | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-02 | VRP | Board and committee portal | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-03 | VRP | Policy and SOP control center | SHOULD | ENTERPRISE | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-04 | VRP | Quality management and CAPA | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-05 | VRP | Risk and compliance register | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-06 | VRP | Project document control | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-07 | VRP | HR document vault | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-08 | VRP | Procurement and vendor dossiers | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-09 | VRP | Secure data-room analytics | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium
VRP-10 | VRP | Industry modules SDK | ADVANCED | EXPANSION | R03 | R33, R29, R30 | R40 | R19 / R40 | Not started |  | Medium

## Risk Register
RISK REGISTER ¦ KMS DELIVERY REVIEW
Risk hypotheses for a product not yet built; Blockers prohibit high-assurance launch. Track validation evidence and residual risk review.
Risk ID | Severity | Failure category | Scenario / impact | Mitigation / decision | Accountable | Affected modules | Required acceptance evidence | Risk state | Evidence / owner notes
K-01 | Blocker | Compromised WordPress bypasses vault | Injected scripts or bridge tokens access plaintext or protected key material. | Independently authenticated signed client; narrow WordPress bridge; hostile-WP tabletop. | R20 | ENC,API,SEC | WP full-RCE scenario cannot obtain private keys, plaintext or new recipients. | Open
K-02 | Blocker | Cross-tenant object reference | Tenant A guesses tenant B document/version ID. | Central authorization with immutable tenant binding, scoped storage, negative tests. | R21 | TEN,IAM,DOC | Fuzz IDs across every API, cache and export path; all blocked. | Open
K-03 | Blocker | Holding admin gets implicit decryption | Group-level role maps to content access or recovery. | Separate administrative plane, content grants and independent trustees. | R02 | TEN,IAM,ENC | Holding admin without explicit grant sees no protected content. | Open
K-04 | Blocker | Key-directory substitution | Server silently replaces an intended recipient public key. | Signed recipient identity, key-transparency or out-of-band device verification. | R20 | ENC,AUT,EXT | Unauthorized recipient enrollment and key swap detected and rejected. | Open
K-05 | Blocker | Losing keys means losing records | E2EE users lose private keys without recovery plan. | Choose no-recovery vs trustee quorum before roll-out; rehearsed recoveries. | R26 | ENC,REC,OPS | Recover permitted tenant with quorum; minority cannot recover. | Open
K-06 | Blocker | E2EE mode leakage through derived content | Previews, thumbnails, search snippets or logs persist plaintext. | Classify derivatives as documents; restrict processing to trusted client. | R20 | DOC,MET,RPT,SEC | DB, queue and object dump contain no protected derivative plaintext. | Open
K-07 | Blocker | Retention and destruction conflict | Legal hold ignored during crypto erasure or object expiration. | Hold priority engine covering backups, versions, exported legal copies. | R12 | REC,ENC,OPS | Held record cannot be deleted by any supported destruction mechanism. | Open
K-08 | Blocker | Server-side malware scanner blind in E2EE | Ciphertext bypasses content inspection but labeled safe. | Mode-specific ingestion/scanning policy, quarantine and residual risk disclosure. | R19 | SEC,DOC,ENC | Opaque E2EE files never get falsely labeled fully server-scanned. | Open
K-09 | Blocker | Approval bypass via workflow races | Reviewer approves one hash while different file is published. | Immutable version/hash binding; maker/checker; idempotent transactional engine. | R33 | WFL,COL,REC | Swap, retry and concurrent approval tests fail closed. | Open
K-10 | Blocker | Compromised key trustee or escrow abuse | Single trustee or platform operator recovers keys covertly. | Independent quorum approvals, audit, dual control and restricted trustees. | R26 | ENC,IAM,RPT | No single account can recover; every approved recovery leaves evidence. | Open
K-11 | Blocker | Broken restore reintroduces access | Backup restoration resurrects expired roles, tokens or deleted documents. | Restore reconciliation; revalidate identity/holds; post-restore policy replay. | R39 | OPS,IAM,REC | Restored tenant honors current revocations and retention policy. | Open
K-12 | Blocker | Malicious conversion payload escapes sandbox | Untrusted PDF/Office exploit reaches keys or tenant data. | Isolated egress-denied workers, strict quotas and patching. | R22 | DOC,SEC | Exploit exercises cannot reach KMS, private networks or other tenants. | Open
K-13 | High | Offline copies remain accessible | User expects remote wipe or revocation to destroy previous files. | Explicit revocation semantics; TTL for future refresh; endpoint management guidance. | R37 | MOB,ENC,IAM | UI and policy disclose unavoidable previously exported/cached copies. | Open
K-14 | High | Cross-subsidiary sharing leaks roles/metadata | Group project accidentally exposes participant members or titles. | Double consent, scoped keys, tenancy-aware notifications and audit. | R21 | TEN,EXT,RPT | Two buyers in a data room cannot discover each other. | Open
K-15 | High | Search and autocomplete existence oracle | Guessable title, timing or counters reveal secret documents. | Metadata classification, authorization at index/query layer and response controls. | R34 | MET,SEC | Search enumeration suite finds no unauthorized hits or suggest tokens. | Open
K-16 | High | AI reads unauthorized prior vectors | Revoked file still available to RAG, cached responses or embeddings. | Entitlement at retrieval and generation, index invalidation and purge policy. | R35 | AIX,MET,IAM | Revoked source is absent from retriever, citation and cached answer. | Open
K-17 | High | Prompt injection triggers dangerous workflow | Malicious document requests export or agent execution. | No autonomous high-impact actions; tools permission-gated; human approval. | R19 | AIX,WFL,API | Prompt-injection tests cannot send data or elevate permissions. | Open
K-18 | High | Group analytics identifies confidential activity | Small group size or filenames permit cross-tenant inference. | Role-scoped aggregates, aggregation thresholds, suppress sensitive dimensions. | R14 | RPT,TEN | Holding reporting reveals no individual classified document history. | Open
K-19 | High | Incorrect legal jurisdiction assumption | System assumes one controller or retention rule fits all entities. | Company-by-country processing inventory; counsel reviewed policy profiles. | R13 | PRV,REC,TEN | Each tenant jurisdiction has signed legal policy mapping. | Open
K-20 | High | Plugin/dependency supply-chain compromise | Signed build or third-party plugin can tamper with bridge or client. | SBOM, provenance, dependency pinning, verified updates and sandboxed bridge. | R38 | SEC,API,OPS | Release artifacts verified and vulnerable dependencies blocked. | Open
K-21 | High | Stale access decision cache | Revoked membership retains long-lived download link or task access. | Short-lived audience-bound grants, event invalidation, recheck at use. | R21 | IAM,API,EXT | Rapid revoke during download/export job fails closed at defined points. | Open
K-22 | High | Privileged support impersonation | Support staff uses break-glass to open business documents silently. | No-plaintext support diagnostics; dual approval and reason-scoped emergency grants. | R27 | IAM,OPS,RPT | Support session cannot see content without explicit reviewed access. | Open
K-23 | High | Inaccurate multilingual permissions | RTL labels reverse meaning or deny appears as allow. | Native security-UI reviews, isolated tokens, locale-specific format tests. | R17 | L10,UX,IAM | 13-language action/permission translations tested with native reviewers. | Open
K-24 | High | Unverifiable digital signature claim | Internal approval labeled qualified/legal e-sign. | Separate approval attestations from vendor/legal e-signature integration. | R13 | WFL,COL,REC | UI and audit distinguish approval log from legally certified signature. | Open
K-25 | High | E2EE prevents legal discovery | Records cannot be produced under lawful order or required audit. | Jurisdiction-approved trustee recovery or documented custodian-produced export. | R13 | ENC,REC,PRV | Legal discovery drill produces permitted records with chain of custody. | Open
K-26 | High | Unauthorized tenant migration | Subsidiary merge/export changes scope or key ownership without approval. | Signed corporate transaction workflow, counsel hold checks, rollback. | R02 | TEN,MIG,ENC | Migration dry-run reconciles keys, content, holds and memberships. | Open
K-27 | High | Third-party editor receives classified plaintext | Office integration or preview vendor sees material unexpectedly. | Mode compatibility matrix, vendor risk review, explicit scoped transfer. | R09 | COL,API,DOC | Zero-Knowledge files cannot open in unapproved cloud editor. | Open
K-28 | High | Broken ownership for knowledge artifacts | Policies go stale and employees attest wrong revision. | Named steward, expiry/review, canonical version and attestation binding. | R15 | KNO,COL,WFL | Attestation tied to exact approved content hash and language. | Open
K-29 | High | Migration brings wrong access | Source ACL mapping creates inappropriate grants in new system. | Dry-run, least-privilege mapping, dual validation and exception resolution. | R42 | MIG,IAM,TEN | All privileged mappings signed off and exceptions resolved. | Open
K-30 | High | No reliable RTO/RPO / backups | Data restored but keys, policy or critical event log missing. | Full restore drills with crypto trustee participation; per-mode SLOs. | R39 | OPS,ENC,RPT | Recover data, versions, permissions, keys and audit consistently. | Open
K-31 | Medium | Localization lacks regional definitions | zh/pt/Arabic calendars and dates inconsistent. | Define locale codes, calendars, plural rules and canonical UTC storage. | R17 | L10,UX,MET | Locale regression covers filenames, dates, search and notifications. | Open
K-32 | Medium | Cost of broad features exceeds budget | Coauthoring, OCR, vector search and 13-language review arrive prematurely. | Dependency-driven release slices and FinOps metering. | R03 | AIX,COL,OPS | Phased roadmap has capacity and cost evidence before commitment. | Open
K-33 | High | Insecure service account scopes | Connector token accesses all tenants or overprivileged storage. | Workload identities with tenant+action restrictions and rotation. | R21 | IAM,API,OPS | Stolen test connector credential cannot read unrelated tenants. | Open
K-34 | High | Privacy requests conflict with immutable copies | Delete request not reconciled with legal holds or backup retention. | Document lawful exceptions, selective deletion and retention flow. | R14 | PRV,REC,OPS | DPO process outputs decision, evidence and actionable execution state. | Open
K-35 | High | Inadequate independent assurance | Development team certifies its own crypto/tenant isolation. | Contract independent crypto and red-team assessments; close blockers. | R25 | ENC,SEC,OPS | Independent retest attests all release blockers closed. | Open

## Architecture Decisions
ARCHITECTURE DECISIONS ¦ KMS DELIVERY REVIEW
Decisions require alternatives, threat/permission impact, sponsor signoff, and immutable ADR before production work on affected modules.
ADR ID | Decision to freeze | Recommended starting direction | Accountable | Module IDs | Decision status | Formal ADR link | Approval date
D-01 | What does a full WordPress compromise mean in threat model? | Assume arbitrary plugin/PHP execution and site administrator; vault remains a separate trust boundary. | R19 | ENC,SEC,API | Open
D-02 | How is Zero-Knowledge code delivered and authenticated? | Separate audited/signed client and independent origin; direct client login; no trust in WP script. | R20 | ENC,MOB,AUT | Open
D-03 | Which documents require Zero-Knowledge Mode? | Default managed mode only when justified; mandate E2EE by classification / subsidiaries. | R02 | ENC,SEC,PRV | Open
D-04 | Is enterprise recovery permitted? | Offer distinct no-recovery and trustee-quorum profiles; truthful assurance claim. | R26 | ENC,REC,OPS | Open
D-05 | Who is accountable for subsidiary data? | Record controller/processor + custodian per legal entity; holding has policy but no implicit decryption. | R14 | TEN,PRV,IAM | Open
D-06 | What is the exact permission evaluation order? | Global immutable safety policy -> tenant boundary -> classification/legal hold -> RBAC/ABAC/ACL -> contextual restrictions; explicit deny wins. | R21 | IAM,TEN,REC | Open
D-07 | Which operations are eligible for break-glass? | Restrict to control-plane admin; no silent document/key recovery; dual authorization. | R27 | IAM,AUT,ENC | Open
D-08 | Which metadata remains visible to servers? | Minimize: tenant, object token, ciphertext size/time where unavoidable; encrypt titles/comments/classification-specific fields. | R20 | MET,DOC,ENC | Open
D-09 | How can confidential content be searched? | Managed: secured index; Zero-Knowledge: trusted-client index with explicitly bounded metadata leakage. | R34 | MET,ENC,AIX | Open
D-10 | What is E2EE malware assurance? | Never assert full server scanning; local scanning + recipient/device policy + quarantine risk disclosure. | R19 | SEC,DOC,ENC | Open
D-11 | What is the approach to external E2EE sharing? | Verified recipient keys; origin approval; purpose, term and immutable share evidence. | R20 | EXT,ENC,IAM | Open
D-12 | Who can authorize a document for legal discovery? | Use counsel-directed custodian export or audited trustee protocol governed by jurisdiction. | R13 | REC,ENC,PRV | Open
D-13 | When does retention outrank deletion? | Counsel-approved precedence; legal hold blocks disposition and key destruction. | R12 | REC,PRV,OPS | Open
D-14 | What are the 13 exact locale codes and variants? | Agree mapping: English, Persian, French, Turkish, Russian, zh-Hans, German, Portuguese variant, Spanish, Hindi, Japanese, Arabic, Armenian; regional options. | R17 | L10,MET,UX | Open
D-15 | What is the definition of digital signing? | Separate internal approvals from applicable qualified digital signature vendors/requirements. | R13 | WFL,COL,REC | Open
D-16 | How do group-wide dashboards preserve confidentiality? | Group sees posture aggregates; document audit requires legally/policy authorized scoped access. | R27 | RPT,TEN,PRV | Open
D-17 | What are target SLO, RTO, RPO and tenant scale? | Benchmark agreed file mix, users, tenant data volumes and geography; publish per-mode targets. | R39 | OPS,DOC,MET | Open
D-18 | Which connectors/cloud editor providers are allowed? | Approved vendor matrix; prohibit unmanaged external document decryption; scope tokens by tenant. | R09 | API,COL,DOC | Open
D-19 | What is the company merger/split procedure? | Approvals from origin/recipient tenant custodians, counsel, security, key trustees as necessary. | R02 | TEN,MIG,ENC | Open
D-20 | When are AI functions permissible? | Opt-in by tenant/classification; managed-only or trusted client local; no training with company data by default. | R14 | AIX,SEC,ENC | Open
D-21 | What is the licensed deployment model? | Private managed service, self-hosted, hybrid; define update chain, residency and customer responsibilities. | R03 | OPS,API,PRV | Open
D-22 | Who makes final production go/no-go decision? | Sponsor + PO after independent security, legal/privacy, records and DR gate sign-offs. | R01 | OPS,SEC,PRV | Open

## Operational Roles
OPERATIONAL ROLES ¦ KMS DELIVERY REVIEW
System-level personas with scope, expressly prohibited access, and segregation of duties. Do not directly equate them to WordPress administrator/editor roles.
Role template | Authorization scope | Powers | Must not grant by default | Conflict-of-duties control | Bounded scope | Role readiness
Holding governance administrator | Group control plane | Provision/suspend entities; set minimum policies. | No default subsidiary-content read or decryption. | Tenant owner + separate board approval for major changes | Yes, unless expressly group/platform scope | Proposed
Holding policy administrator | Group control plane | Manage mandatory security/retention configuration baselines. | Cannot grant own document access; policy cannot defeat holds. | Risk/records approval for exceptions | Yes, unless expressly group/platform scope | Proposed
Holding security oversight | Group security | View posture, incidents and scoped security events. | No automatic content; sensitive tenant audit fields redacted. | Separate from holder of recovery keys | Yes, unless expressly group/platform scope | Proposed
Group internal auditor | Group audit | Review approved controls/evidence and aggregates. | No default business document access. | Independence from admins and approvers | Yes, unless expressly group/platform scope | Proposed
Platform operator / SRE | Infrastructure only | Deploy, monitor, scale and restore infrastructure. | No routine decrypted document content or user impersonation. | Dual control on critical production changes | Yes, unless expressly group/platform scope | Proposed
Subsidiary owner | One subsidiary | Approve local governance/tenant closure and custodians. | Cannot weaken global minimum controls. | Cannot self-approve exceptional disclosure | Yes, unless expressly group/platform scope | Proposed
Subsidiary administrator | One subsidiary | Invite users, create groups and configure libraries. | No universal decrypt right; no cross-tenant reach. | Role-grant approvals for high privileges | Yes, unless expressly group/platform scope | Proposed
User and group administrator | One subsidiary | Manage memberships, employment-state updates. | No content read via membership management alone. | No self-privilege escalation | Yes, unless expressly group/platform scope | Proposed
Role / access policy manager | One subsidiary | Create custom roles and ACL templates. | Cannot override legal holds and group hard-denies. | Another approver for high-risk policy changes | Yes, unless expressly group/platform scope | Proposed
Department manager | Own department | Manage own teams and delegated workspaces. | Delegation limited to preset domain and role subset. | No grant beyond own authority | Yes, unless expressly group/platform scope | Proposed
Records manager | One subsidiary / record set | Control classification, retention and disposition. | Cannot unilaterally lift legal hold. | Disposition reviewer separate from executor | Yes, unless expressly group/platform scope | Proposed
Legal-hold officer | Approved matters | Place/lift holds under legal process. | No content access unless separately authorized. | Counsel approval and dual-review on releases | Yes, unless expressly group/platform scope | Proposed
Privacy officer | Legal entity / approved scope | Process privacy requests, DPIAs and data mappings. | No blanket document access for privacy role. | Lawful hold/exemption review | Yes, unless expressly group/platform scope | Proposed
Subsidiary security officer | One subsidiary | Monitor local access, incidents and classification alerts. | No default access to protected documents. | Independent security and incident review | Yes, unless expressly group/platform scope | Proposed
Document controller | Assigned library | Register, classify, version and release controlled records. | Cannot circumvent approval or holds. | Separate approver for publication | Yes, unless expressly group/platform scope | Proposed
Document custodian | Named document or collection | Own access, classification and retention contact. | No unrestricted group-wide rights. | Share approval for restricted documents | Yes, unless expressly group/platform scope | Proposed
Contributor / editor | Granted documents | Upload and edit working copies. | Cannot approve own controlled release. | Maker/checker on controlled documents | Yes, unless expressly group/platform scope | Proposed
Reviewer / commentator | Assigned documents | Comment, request changes, review versions. | No self-grant or release rights. | Independent of author where required | Yes, unless expressly group/platform scope | Proposed
Approver / publisher | Assigned workflow | Approve immutable hashes and publish approved revision. | No edit of signed approved bytes. | Must meet quorum / SoD | Yes, unless expressly group/platform scope | Proposed
Knowledge steward | Assigned KB space | Maintain canonical articles and scheduled reviews. | No cross-entity search or publish beyond grants. | Independent approval of controlled SOPs | Yes, unless expressly group/platform scope | Proposed
Workflow designer | Approved workflow domain | Configure versioned state machines/routing. | Cannot approve by modifying live workflow. | Change approval plus staging simulation | Yes, unless expressly group/platform scope | Proposed
Read-only viewer | Granted documents | View permitted content and acknowledge required reading. | No editing, exports or shares unless explicitly granted. | Document-specific authorization | Yes, unless expressly group/platform scope | Proposed
External guest / auditor | Specific collaboration | Review invited folders / evidence packages. | No tenant enumeration or rights to other guests. | Identity validation, expiry, NDA if needed | Yes, unless expressly group/platform scope | Proposed
Service/workload identity | Specific tenant + API scopes | Execute narrow automation and connector jobs. | No interactive login; no universal multi-tenant API key. | Secret rotation and workload approval | Yes, unless expressly group/platform scope | Proposed
Key-recovery trustee | Key domain + approved case | Participate in quorum recovery, never solo. | No routine content access or invisible recovery. | Quorum, legal basis, immutable event | Yes, unless expressly group/platform scope | Proposed
Emergency incident responder | Time-limited scope | Contain incidents and revoke sessions. | No automatic plaintext/key bypass; only approved exceptional grants. | Ticket, dual control and postmortem | Yes, unless expressly group/platform scope | Proposed

## Release Gates
RELEASE GATES ¦ KMS DELIVERY REVIEW
Go/no-go requires independent crypto and penetration evidence. Business or schedule pressure cannot override unresolved security blockers.
Gate | Definition / milestone | Signoff role | Exit criteria | Evidence required | Gate status | Evidence link
G0 | Charter and authority | R01 | Funding/risk appetite; 10 legal entities and operating jurisdictions; responsible data controllers named. | Approved charter, entity list, governance and decision log. | Not started
G1 | Threat model and design | R19 | Agree WordPress threat boundary, protection modes, data flows, abuse cases and legal constraints. | Reviewed diagrams; ADRs; product-mode compatibility matrix. | Not started
G2 | Tenant and access proof | R21 | Prove isolation and formal permission order, independent identity, limited WordPress bridge. | Policy test harness; API fuzzing results; negative tenant tests. | Not started
G3 | Cryptographic assurance | R25 | Confirm independent trusted-client distribution, E2EE protocol, key identity, recovery and trust limits. | Third-party crypto report; protocol vectors; WordPress-RCE red-team scenario. | Not started
G4 | Core document lifecycle | R03 | Upload, quarantine, immutable versions, approval, audit and download all tested end-to-end. | Traceability to core requirements; E2E automation; malicious-file tests. | Not started
G5 | Governance and resilience | R12 | Retention/holds/DSRs, 13 languages, WCAG, backup/keys/identity restore all validated. | Legal/privacy signoffs; translated UAT; DR and retention tabletop. | Not started
G6 | Subsidiary pilot | R11 | Test multiple separate subsidiaries (including RTL), different roles and cross-company share path. | Signed tenant UAT, support runbooks and resolved high-severity defects. | Not started
G7 | Independent production go/no-go | R01 | No unresolved critical vulnerabilities; approved exceptions; operations and incident readiness. | Independent pen-test, security signoff, restore results and release checklist. | Not started
G8 | Enterprise expansion change gate | R03 | New AI, coauthoring, mobile, and vertical modules receive mode-specific security/review tests. | Per-module ADR, impact assessment, signed regression and training. | Not started

## Baseline Revisions
BASELINE REVISIONS ¦ KMS DELIVERY REVIEW
Escalations are conditional, not claims that prior features were missing. Update the original 346-feature catalog after architecture/legal approval.
Existing ID | Conditional priority change | Reason for change | Accountable | Review status | Decision/evidence
ENC-08 | SHOULD -> launch-blocking for high-assurance E2EE | Verified recipient key identity or equivalently strong external verification must exist before any sensitive cross-device/cross-company sharing. | R20 | Open
RPT-04 | SHOULD -> launch-blocking for regulated/auditable deployment | Integrity evidence must be tamper-evident and stored outside WordPress administration. | R27 | Open
OPS-05 | SHOULD -> operational go-live prerequisite | RTO/RPO targets and successful restorations are necessary to know whether production is supportable. | R39 | Open
TEN-13 | SHOULD -> mandated where contractual/legal residency applies | Residency must cover backups, caches, metrics, keys, support and subprocessors, not only primary objects. | R14 | Open
PRV-03 | SHOULD -> mandated if subsidiaries face distinct jurisdictional regimes | Tenant-specific legal profiles needed to avoid invalid uniform retention/disclosure rules. | R13 | Open
AUT-04 | SHOULD -> strongly recommended go-live control for enterprise employees | SCIM/event-driven provisioning and timely departure suspension reduce orphan accounts. | R21 | Open
IAM-16 | SHOULD -> mandatory for privileged and sensitive periodic reviews | Management needs auditable certifications of elevated access and stale external grants. | R27 | Open
REC-09 | SHOULD -> mandatory if a record class must be WORM/immutable | Must be technical rather than process-only where law/contract mandates immutability. | R12 | Open
REC-13 | SHOULD -> mandatory if eDiscovery obligations apply | Zero-Knowledge recovery/export plan must be chosen before regulated content is encrypted. | R13 | Open
AIX-13 | SHOULD -> mandatory before enabling AI | AI inputs, outputs, source access and provider actions must be auditable. | R14 | Open
AIX-16 | SHOULD -> mandatory before sending content to an external model | Provider retention, training exclusion, subprocessors and DPA must be enforceable. | R14 | Open
MOB-02 | SHOULD -> mandatory if an independent native client is the selected E2EE trust model | Strong separation from WordPress requires shipped, signed and independently verified client code. | R37 | Open
SEC-07 | SHOULD -> assess as mandatory under high ransomware threat | Immutable versions / offline restoration are necessary even if anomaly detection remains optional. | R23 | Open
PRV-04 | SHOULD -> mandatory when applicable personal-data rights are triggered | Subject-rights processes cannot be postponed merely because feature phase says Enterprise. | R14 | Open

## Acceptance Scenarios
ACCEPTANCE SCENARIOS ¦ KMS DELIVERY REVIEW
Threat-model-driven and cross-role acceptance tests. Add automated test URLs, external assessment evidence and release gate mapping.
Test ID | Test family | Scenario | Required evidence | Affected modules | Status | Test artifact
T-01 | Isolation | Tenant A admin guesses Tenant B document/version/metadata/queue ID | All paths deny and independent audit has evidence. | TEN,IAM,API,RPT | Not run
T-02 | E2EE code integrity | WordPress administrator modifies WP theme/plugin to serve malicious JS | Trusted client neither executes injected code nor releases keys or plaintext. | ENC,API,MOB | Not run
T-03 | Recipient authenticity | Attacker substitutes public key in key directory | Trusted client blocks unverified recipient and alerts owner. | ENC,AUT,EXT | Not run
T-04 | Privilege escalation | Subsidiary admin grants self group-wide auditor/escrow role | Permission creation rejected; privileged change requires separate approval. | IAM,TEN | Not run
T-05 | Permission race | Revoke user while export, preview, workflow and search requests run | Defined consistency window enforced; no fresh unauthorized copy completed after final check. | IAM,DOC,WFL | Not run
T-06 | Malicious document | Upload malformed Office/PDF designed to exploit converter | Quarantine and isolated sandbox prevents network/file/key compromise. | DOC,SEC | Not run
T-07 | Confidential preview | Request E2EE preview via ordinary WP dashboard | System presents independent trusted viewer; no WP origin sees plaintext. | ENC,DOC,UX | Not run
T-08 | Legal hold | Place hold, then attempt deletion, retention expiry and crypto-erasure | All destructive paths deny with preserved evidence. | REC,ENC,OPS | Not run
T-09 | Key recovery | Lose device; request recovery with one trustee instead of quorum | Fails until independently approved quorum, then audited recovery succeeds. | ENC,AUT | Not run
T-10 | Device compromise | User loses previously synced phone and is deprovisioned | New versions and future distribution denied; prior offline data limitation displayed. | MOB,ENC,IAM | Not run
T-11 | Cross-company project | Tenant A shares selected file with Tenant B group | Named members only, approvals and keys verified, no blanket B rights. | EXT,TEN,IAM | Not run
T-12 | Audit tampering | WP admin tries to delete download and authorization failure events | Independent audit continues to show original events and tampering alarm. | RPT,SEC | Not run
T-13 | AI leakage | Revoked document exists in vector index and cached answer | Retrieval, cache and output no longer expose that source. | AIX,MET,IAM | Not run
T-14 | Prompt injection | Malicious document instructs AI agent to email private file | No autonomous export, tool grant or workflow approval. | AIX,WFL,SEC | Not run
T-15 | Backup restore | Restore tenant from old snapshot including revoked roles | Reconciles current policy/hold/revocations before opening restored tenant. | OPS,IAM,REC | Not run
T-16 | Localization | Persian and Arabic RTL document sharing, approval and permission UI | Native validation finds no reversed affordances/IDs; screen-reader correct. | L10,UX | Not run
T-17 | Migration | Import historic documents with mismatched identity and denied ACLs | Dry run reports exceptions; no overly broad grants; provenance preserved. | MIG,IAM | Not run
T-18 | Company separation | Split one subsidiary into two while legal hold exists | Approved custody, key rewrap, audit trail and retention remain valid. | TEN,REC,ENC | Not run
T-19 | Cloud editor | Attempt to open E2EE file in external online editor | Blocked unless approved conversion and explicit authorized disclosure. | COL,ENC,API | Not run
T-20 | Disaster recovery | Simulate regional outage with KMS outage and independent logs | System follows declared RTO/RPO without fail-open; keys/audit recover. | OPS,ENC,RPT | Not run

## Design Conflicts
DESIGN CONFLICTS ¦ KMS DELIVERY REVIEW
Confidentiality trade-offs need explicit feature-mode behavior, consent and product disclosure rather than silent functionality fallback.
Conflict ID | Incompatible expectations | Required architecture / product trade-off | Joint owners | Decision status
CF-01 | Zero-Knowledge files vs server OCR/search/AI | Use trusted-client processing; otherwise managed mode after explicit classification approval. | R20 / R34 / R35 | Open
CF-02 | Zero-Knowledge malware inspection vs opaque ciphertext | Admit reduced server assurance; client scan, device posture, staging/quarantine and policy restrictions. | R19 / R32 | Open
CF-03 | Strong confidentiality vs forgotten keys | Choose no recovery (permanent loss possible) or independently governed quorum recovery (extra access path). | R20 / R26 | Open
CF-04 | Authorization revocation vs offline access | Revoke future delivery; clearly disclose inability to erase previously copied plaintext or keys. | R21 / R37 | Open
CF-05 | Group central oversight vs subsidiary confidentiality | Keep control-plane and document-key permissions separate; aggregated group reporting. | R02 / R21 | Open
CF-06 | Legal hold vs right to erasure / crypto erasure | Apply jurisdiction-specific priority with recorded legal justification, review and execution gates. | R12 / R13 / R14 | Open
CF-07 | E2EE vs court-directed eDiscovery | Adopt legal custodian export or trustee recovery procedure; do not imply invisible server decryption. | R13 / R20 | Open
CF-08 | Browser client E2EE vs compromised code delivery | Use independently hosted signed client and verification; do not trust JavaScript supplied by WordPress. | R20 / R37 | Open
CF-09 | Enterprise coauthoring vs E2EE | Use locally trusted E2EE editing protocol or classify as managed collaboration; do not silently downgrade. | R30 / R37 | Open
CF-10 | AI answers vs authorization changes | Re-evaluate permissions per source and at answer time, purge embeddings and caches, constrain outputs. | R35 / R21 | Open
CF-11 | Audit richness vs privacy and subsidiary secrecy | Redact/minimize payloads; permission-tiered logs; independent integrity and retention. | R27 / R14 | Open
CF-12 | Digital approval vs legal electronic signature | Separate workflow acknowledgments from vendor-backed signature evidence and jurisdiction-specific requirements. | R13 / R33 | Open
CF-13 | Third-party editor vs content confidentiality | Vet data handling and prevent plaintext transfer of protected files to unapproved editors. | R09 / R20 | Open
CF-14 | Public KB publishing vs hidden tenant content | Use approved declassification with separate public projection and no anonymous backdoor queries. | R15 / R19 | Open
CF-15 | Migration convenience vs verified historical entitlements | Use signed dry-runs, least-privilege ACL mapping, dual approval and auditable exceptions. | R42 / R21 | Open

## References
REFERENCES ¦ KMS DELIVERY REVIEW
Authoritative design references. Jurisdictional laws and standard versioning require explicit legal/security review.
Reference | Engineering use | Official / primary-source URL
OWASP ASVS 5.0.0 | Application security verification criteria | https://owasp.org/www-project-application-security-verification-standard/
OWASP Multi-Tenant Security Cheat Sheet | Tenant boundaries across storage, cache, queues, logs and APIs | https://cheatsheetseries.owasp.org/cheatsheets/Multi_Tenant_Security_Cheat_Sheet.html
OWASP Authorization Cheat Sheet | Deny by default, least privilege, object authorization | https://cheatsheetseries.owasp.org/cheatsheets/Authorization_Cheat_Sheet.html
OWASP Cryptographic Storage Cheat Sheet | Key separation, authenticated encryption and key lifecycle | https://cheatsheetseries.owasp.org/cheatsheets/Cryptographic_Storage_Cheat_Sheet.html
NIST SP 800-63-4 (Final, July 2025) | Digital identity, authentication and federation | https://csrc.nist.gov/pubs/sp/800/63/4/final
NIST SP 800-57 Part 1 Rev 5 | Cryptographic key management planning | https://csrc.nist.gov/pubs/sp/800/57/pt1/r5/final
NIST SP 800-218 v1.1 (Final); v1.2 is draft as of Oct 2026 | Secure software development / supply chain | https://csrc.nist.gov/projects/ssdf/publications
WordPress REST API Handbook | Permission callback and endpoint security | https://developer.wordpress.org/rest-api/extending-the-rest-api/adding-custom-endpoints/
WordPress Security Nonces Handbook | Nonces are not authorization / identity | https://developer.wordpress.org/apis/security/nonces/
W3C WCAG 2.2 | Accessibility acceptance benchmark | https://www.w3.org/TR/WCAG22/
ISO 15489-1:2016 | Records governance principles | https://www.iso.org/standard/62542.html
UK ICO Right to Erasure | Lawful erasure may have applicable exceptions; determine jurisdiction | https://ico.org.uk/for-organisations/uk-gdpr-guidance-and-resources/individual-rights/individual-rights/right-to-erasure/
Mozilla, Trustworthy JavaScript for the Open Web (2026) | Server-supplied JavaScript integrity and E2EE delivery limitation | https://hacks.mozilla.org/2026/05/trustworthy-javascript-for-the-open-web/

## Dashboard
ENTERPRISE KMS ¦ DELIVERY GOVERNANCE SNAPSHOT
Companion to the existing 346-feature blueprint. Editable role assignments, traceability, risks, architectural decisions, module review and go-live evidence.
Implementation hats | 44 | Risk profile | Count
Operational personas | 26 | Blocker | 12
Feature IDs | 346 | High | 21
Feature modules | 22 | Medium | 2
Tracked risks | 35
Architecture decisions | 22
Release evidence gates | 9 | Requirement delivery state | Count
Security scenarios | 20 | Not started | 346
|  | In design | 0
|  | In development | 0
RELEASE RULES |  | In test | 0
No WordPress admin automatically receives decryption privileges. |  | Accepted | 0
Zero-Knowledge does not imply server-side OCR, full-text AI, or malware scanning.
A lost private key may be unrecoverable unless trustees are deliberately configured.
Blocker findings require independent verification before production go-live.
Priority promotions are conditional: adopt per jurisdiction and threat model.
WORKFLOW: Assign team owners → resolve decisions → update 346 feature statuses → execute acceptance tests → close risks → sign release gates.

## Mode Compatibility
MODE COMPATIBILITY ¦ KMS DELIVERY REVIEW
Two security modes have different permissible processing and guarantees. Product UX must communicate compatibility and prevent silent security downgrade.
Capability | Managed Secure Mode | Zero-Knowledge Mode | Implementation constraint | Linked feature IDs
File upload / versioning | Available; service encrypts objects with external KMS | Available; trusted client encrypts before upload | Verified document version and per-version key | DOC-01, ENC-03
Previews and thumbnails | Sandboxed conversion with controlled temporary plaintext | Only trusted client local rendering, no WordPress-served plaintext | Malicious file parser and derivative confidentiality | DOC-21, SEC-05, ENC-17
Content OCR | Isolated server worker allowed by policy | Only trusted-client-side OCR or explicitly disclosed declassification | CPU/device limits, extracted text confidentiality | MET-08, ENC-14
Full-text search | Permission-trimmed protected server index | Trusted-client local/private index; no ordinary server plaintext index | Encrypted metadata and authorization at search time | MET-06, MET-07
Metadata and filenames | Encrypted storage with designated searchable fields | Encrypt sensitive fields; explicitly document minimum metadata leakage | Search existence or timing side channels | ENC-14, MET-01
Virus/malware inspection | Pre-publication server sandbox scanner | Client checks and policy quarantine; not equivalent to server scan | Residual risk warning, device posture | SEC-04
Data-loss prevention | Server + policy enforcement on content and exports | Client-local rules and metadata limits; cannot guarantee remote enforcement | Screen capture and prior exports remain out of reach | SEC-02, SEC-03
AI summaries / Q&A | Optional policy-trimmed service; reviewed provider | Not by ordinary server; local trusted client/model only if independently reviewed | Prompts, embeddings, citations and model retention | AIX-02, AIX-03, AIX-16
Semantic vector search | Secured index, re-authorize every retrieved item | Trusted-client model/index only or explicitly approved leakage-risk protocol | Vector reconstruction and revoked-source purge | AIX-04, IAM-17
Editing and coauthoring | Approved cloud editors with contracts | Only reviewed E2EE-aware editor/protocol | No silent switch to managed mode | COL-05, COL-06
Annotations and comments | Protected service data subject to ACLs | Encrypt client-side, recipient-access keys | Do not leak through activity notifications | COL-07, ENC-14
Approval workflow | Server can verify hashes + route; no universal plaintext required | Server routes hashes/ACLs; client signs/countersigns without uploading plaintext | Signature and attestation legality separate | WFL-07, COL-14
Digital legal signatures | Approved external eSignature vendor as legally required | Trusted client or explicit disclosed transfer with consent | Jurisdiction-specific evidence requirements | WFL-14
External and cross-tenant shares | Recipient identity, scoped service grants and expiration | Client-verified recipient public key + rewrapping | Origin permission, guest identity and key authenticity | EXT-04, ENC-09
Data rooms | Service-managed data room with granular roles | Trusted client data room for selected E2EE docs | Two-bidder isolation, forensic logging | EXT-03
Legal holds / retention | Service immutability and retention engine | Hold ciphertext and wrap keys; discovery requires authorized client/trustee | Prevent accidental crypto-erasure of held content | REC-05, ENC-18
Legal discovery exports | Counsel-approved auditable service export | Custodian client export / trustee governance if allowed | Chain of custody and justified access | REC-13
Key backup and recovery | KMS/HSM separation with recoverable KEKs | Trustee-quorum or no recovery, explicitly labeled | Cannot simultaneously promise no recovery and enterprise escrow | ENC-12
Revocation | Deny future token/API access and optionally protected re-encryption | Stop future distribution; rekey future versions; prior downloaded files persist | No impossible remote deletion guarantee | ENC-11, IAM-17
Mobile / offline | Encrypted device cache, token expiry, remote best-effort wipe | Hardware-backed keys where possible and signed trusted app | Revocation cannot remove previously offline plaintext | MOB-04, MOB-06
Backups / restore | Encrypt, restore data + keys + permissions + evidence | Back up ciphertext; separately protect trustees/key recovery material | Protect residency and current access state after restore | OPS-06, ENC-12
Support diagnostics | Sanitized operational diagnostics; temporary privileged access reviewed | Ciphertext-only support; no plaintext from WordPress | No privileged impersonation without approvals | OPS-17, ENC-17
Analytics and activity dashboards | Role-filtered events with limited content fields | Ciphertext-safe event metadata; do not infer secret titles | Confidentiality of small tenant aggregates | RPT-06, RPT-10